## Status
Document | Status
Requirement | Frozen
Database Design | Frozen
Database Construction | Frozen
Application Design | Completed
Application Construction | Completed
UI Design | Completed
UI Constuction | Completed

## Project Timeline
Phase | Activity | Timeline - Expected |  | Timeline - Actual
|  | From | To | From | To
Requirement Modeling |  |  |  | 2016-01-02 | 2016-01-04
Back-End | Database Design |  |  | 2016-01-05 | 2016-01-22
| Database Construction |  |  | 2016-01-21 | 2016-01-22
| Application Design |  |  | 2016-01-22 | 2016-02-24
| Application Construction |  |  | 2016-02-02 | 2016-02-24
Front-End | UI Design |  |  | 2016-02-06 | 2016-02-24
| UI Construction |  |  | 2016-02-16 | 2016-02-24
Note on B7: Author: 5/Feb First test on Search functionality completed successfully without any hitches, I am very very happy

## Milestones
Date | Milestone
2016-01-02 | Officially kick started the project
2016-02-05 | Completed the first part of the back end and tested successfully, it ran successfully without any bugs :) at the first try :D
2016-02-24 | Coding phase ended for Version 1 of dictionary. Unit and Initial testing is successful and all components are working.

## log
Date | Remark
2016-02-16 | Started with creating GUI in java awt and the positioning of the components manually so that the expected desigh would be achived is really tedious thing to do and nothing much is gained by doing so, stopped with AWT and started with swings, will revisit once I have time
2016-02-24 | I am happy beacause this the first project I stared for my future and it went smoothely. I belive the this is because I spent most of the time in modeling and designing, as said in the Software Enginerring by Roger S. Pressman

## Sheet3
Not Started
In Progress
Completed
Frozen