## Status
Document | Status | Code | Status
Requirement | Frozen | Database | Frozen
Database Design | Frozen | Backend | Frozen
Backend Design | Frozen | GUI | Frozen
GUI Design | Frozen

## Project Timeline
Activity | Timeline - Expected |  | Timeline - Actual
| From | To | From | To
Database Design |  |  | 2016-02-25 | 2016-02-26
Database Design - Patch 1 |  |  | 2016-02-27 | 2016-02-27
Database Construction |  |  | 2016-02-26 | 2016-02-27
Database Design - Patch 2 |  |  | 2016-03-13 | 2016-03-14 | Color code | Description
Backend Design |  |  | 2016-02-27 | 2016-03-01 |  | Activity Completed
Backend Construction |  |  | 2016-03-03 | 2016-03-16 |  | Activity In progress
UI Design |  |  | 2016-03-16 | 2016-05-04 |  | Activity Not Started
UI Construction |  |  | 2016-03-17 | 2016-05-04

## Milestones
Date | Milestone
2016-02-26 | Database design and its construction is completed
2016-02-27 | Data import completed
2016-03-01 | Backend design completed
2016-03-16 | Backend coding is, in a lighter sence, over. Changes might be made during UI coding
2016-05-04 | GUI coding complete
Application tested

## log
Date | Remark
2016-02-25 | Started with version 1.1 of dictionary, then changed the version number to 2.0 because the complete software is recoded
Created Version overview document
2016-02-26 | Finalized naming convensions for DB objects
Design and construction of database is complete and started with data import
Updated Version overview document
Updated the design template of Timeline and Status sheet 1. Added activity color code 2.Removed few enteties from the table in Status sheet
2016-02-27 | While importing data into DB found out that I miseed a minor necessary feature sequence in which set of context of different of part of speech appear. Added a new activity Database Design - Patch 1
Completed Database Design - Patch 1 and completed data import
2016-02-29 | Thie file of the Class design I worked on for two days got corropted, probably because I was messing with the setting tab of AgroUML, so there goes my two day work :)
2016-03-01 | Completed the Class Design for the backend
2016-03-03 | Started with the backend coding
2016-03-13 | While doing backend coding found a design flaw in the database design and started with the Database Design - Patch 2.
2016-03-14 | Database design - Patch 2 is completed and the database has be updated with the new design
2016-03-15 | Completed unit test for the backend search and it was successsfull and had just one coding error.
2016-03-16 | Backend coding is over, further changes is depend on UI needs
Completed UI design
2016-04-24 | After a long pause started with the UI Coding. Was studying concepts of JAVA I previously ignored.
2016-05-04 | Completed the coding
Tested and found few bugs
Bugs fixed and tested again

## Sheet3
Not Started
In Progress
Completed
Frozen